## Sheet1
Canara Bank Mobile Bugs
S.no | Module | Description | Status | Remarks | Bug Id
Ver 1.2.0 | 17-10-2025
1 | APK Name | Both BC and BO APK have the same name | New | feedback | 86d0na1br
2 | BO->New SHG->New to Canara Bank | State and District are not showing | New | fixed | 86d0nb301
3 | BO->New SHG->New to Canara Bank | Mobile number otp verification, there is no toast message showing if otp verified successfully | New | fixed | 86d0nb6u4
4 |  | App crashes sometimes | New | fixed
5 | all calendar | ex: the SHG Formation date is selected from the calendar, if I click the calendar again, it must show the selected SHG formation date not the present date | New |  | 86d0nbzqx
6 | BO->New SHG->Verification | State and District are not showing | New | fixed | 86d0nc037
Ver 1.0.3(BC) Ver 1.2.0(BO) | 22-10-2025
1 | in BO and BC->OTP | After enter otp, when I click the back, the cursor in the same box | New | fixed | 86d0pn0bk
2 | Both in BO and BC->After Onboarding->Meeting->Minutes of meeting | All the content is duplicated | New | fixed | 86d0pmzrx
3 | BC ->Existing SHG | The select button must not show in BC without the group being verified by the BO | New | fixed
4 | BO->Cut off screen | I added MFI Bank details. If I try to delete the bank details, it shows "Failed ". | New | fixed | 86d0pn22p
5 | BC ->cut off date | in the Bank balance screen and Balance sheet, the step numbers are mismatched | New | fixed | 86d0ppck1
6 | BO->SB Account Opening->SB A/c Pending | The onboarding is pending, but the group name is listed in the SB A/c pending. | New | Fixed | 86d0pq9jq
Ver 1.0.3(BC) Ver 1.2.0(BO) | 23-10-2025
1 | BO->SB Account Opening->SB A/c Pending | once I finished e-sign,Again i can create the SB A/c for that group | New | fixed | 86d0q10h4
2 | BO->SB Account Opening->SB A/c Approved | It shows "Failed" | New | fixed | 86d0q113a
3 | BC onboarding->Cut off screen | After submitting the cut-off date, if I close the app and log in again, the cut off date is empty | New | fixed | 86d0q2auj
4 | BC and BO Member add | After adding the member and going back to the SHG profile, click send otp, don’t enter the otp then click back button it move to the member profile screen, now click the edit. It shows white screen | New | Fixed | 86d0q2b23
5 | BO | Role, Mobile number and Last Login are not showing | New | fixed
6 | BC and BO Member add | in the member, we can add a member without uploading the member profile image | New | fixed | 86d0q3hxn
Ver 1.0.4(BC) Ver 1.2.1(BO) | 24-10-2025
1 | BC onboarding | in Sub District it shows "No data found" | New | fixed | 86d0qb1v6
2 | BC->after onboarding | The member profile must not be visible in BC | New | fixed | 86d0qc6wr
3 | BO->SB A/c Pending | "SB account", account "A" must be in capital letter | New | fixed | 86d0qc7x0
4 | BO-> Cut off date | In the cut-off date screen, remove the SHG loan, Federation/MF bank details | New | fixed | 86d0qc8ca
5 | BO->Existing SHG | It takes a long time to load the SHG list | New | feedback | 86d0qc90b
6 | BO->Existing SHG | After typing the group name, the keypad is not closed | New |  | 86d0qc9h1
7 | BC->Existing SHG | If I select the group, in the OTP page, the content must align in the center in the tab. | New |  | 86d0qca5u
8 | BC and BC ->All otp screen | otp expired, without resending the otp, I can log in with the expired otp | New |  | 86d0qcb7e
9 | BC and BC ->login otp | Countdown and Resend otp are not properly visible | New | fixed | 86d0qcubv
10 | BC and BC->Ondoarding->new | Mobile number verification, after entering the otp and verifying the message is shown, but the Countdown is still running | New | fixed | 86d0qec6n
11 | BC and BO->After onboarding->group profile->Add Bank | After validation, add the toast message "Validation successfully" | New | fixed | 86d0qef7m
12 | BO->Existing SHG->group profile | if I add another bank, after validation, the Beneficiary name must show below the validate button | New | fixed | 86d0qefee
13 | BC and BO->After onboarding->group profile->Add Bank | after validate all the bank details, click submit button it shows "Please click validate" | New | fixed | 86d0qefnq
14 | BC -> After onboarding->Meeting->Attendance | if I click submit button without upload group photo, change the toast message to this "Please upload group photo for attendance" | New | fixed | 86d0qegvm
15 | BC-> After onboarding->Meeting->Minutes of meeting | if I click submit button without upload Resolution photo, change the toast message to this "Please upload resolution photo for minutes of meeting" | New | fixed | 86d0qekm3
16 | BC-> After onboarding->Meeting->Minutes of meeting | In the upload screen if I click done button without upload any photo it shows "please add a group photo for attendance" change this to "please add a resolution photo for minutes of meeting" | New | fixed | 86d0qewhr
17 | BO and BC ->Onboarding | remove the "Member financial screen" | New | fixed | 86d0qfhjx
18 | BO->Onboarding->Verification | Only the onboarding-finished group must be listed in the Verification | New | fixed | 86d0qfj1z
19 | BO->Onboarding-> Verification and Existing SHG | in the group list search add the search button | New | fixed | 86d0qfjby
20 | BC->Existing SHG->select the group | In the otp screen, After enter otp, when I click the back, the cursor skip the 4 and 5 box | New | fixed | 86d0qfp78
Ver 1.0.4(BC) Ver 1.2.1(BO) | 27-10-2025
1 | BC->Existing SHG->select the group | After enter otp, the keypad must be closed | New | Fixed | 86d0r0hmp
2 | BC-> After onboarding->Meeting->Minutes of meeting->internal loan | if I click the submit button, it shows "Please try again" | New | fixed | 86d0r20an
3 | BO->After onboarding | if I clike profile, it loads after re-login it works properly | New | fixed | 86d0r5z2q
Ver 1.0.4(BC) Ver 1.2.1(BO) | 28-10-2025
1 | BC->New SHG->New to canara bank->Add Bank | it shows "No data found" | New | fixed | 86d0rfqy1
2 | BC->after onboarding verified | BC can't modify the group profile | New | fixed | 86d0rg5uz
3 | BO->After onboarding verified | BO make any changes in group or member profile, must done OTP verification | New | fixed | 86d0rkwwa
4 | BC-> Login OTP screen | I can't enter otp if the curser in the entered otp | New | fixed | 86d0rm88u
5 | BC->Exisiting SHG ->select the group->transaction | the loading take some time | New | fixed | 86d0rmr9t
6 | BO->Creadit Linkage | if select pending or post sanction visit or Disbursed loan , it load but not give any resonce | New | Post-sanction visit and disbursed loan are not fixed | 86d0rmz7e
Ver 1.0.4(BC) Ver 1.2.1(BO) | 29-10-2025
1 | BC->Existing SHG ->Onboard pending group->Bank details | If I click the bank name, it shows "No data found" | New | fixed | 86d0rzt50
2 | BC->Existing SHG ->Onboard pending group | the pending group has bank details, in the bank details, I click the proof view button, but there is no response | New | fixed | 86d0rzjp0
3 | BC->Existing SHG ->Onboard pending group | If I try to change the village, it shows "Please select taluk" but the taluk is already selected. | New | fixed | 86d0rzf2t
4 | BC->Existing SHG ->Onboard pending group | I can't edit the formation date | New | fixed | 86d0rzekr
5 | BC->Existing SHG->select the group | in the OTP, only the number keypad must show in tab | New | fixed | 86d0t4776
Ver 1.0.4(BC) Ver 1.2.1(BO) | 30-10-2025
1 | BO-> Existing SHG | it shows "SHG not assigned, do you want to add new SHG?" | New | fixed | 86d0te4kq
2 | BO and BC ->Transaction | Non-paid member count showing wrongly, when I come back to transaction again | New | fixed | 86d0teja5
3 | BC->Minutes of meeting ->internal loanj | after enter the loan amount, click submit button, it shows "Please try again" | New | fixed | 86d0tek62
4 | BC->Bookkeeping->Payment ->Disbursement | in the minutes of meeting internal loan is not done it show "Please try again" but in the Disbursement resolution there are 3 resolution for that month | New | fixed | 86d0tf0hz
5 | BC->Minutes of meeting | meeting count is not correct | New | fixed | 86d0tf2n5
6 | BO and BC ->after onboarding-> group profile->Bank detail | I can add the same Bank account number and branch | New | fixed | 86d0thhkn
7 | BO and BC ->after onboarding-> group profile->Bank detail | I can't delete the bank details | New | fixed | 86d0thj40
Ver 1.0.5(BC) Ver 1.2.3(BO) | 2025-03-11
1 | BO->Existing SHG | if the pending group has bank details, in the bank details, I click the proof view button, but there is no response | New | fixed | 86d0uppm9
2 | BO ->After verified ->group profile-> Address | if I edit the address and click submit button, it shows "Please select sub district" | New | fixed | 86d0uqrr9
3 | BO ->After verified ->group profile-> Bank details | i can edit the bank details without click the edit button | New | fixed | 86d0uqx2y
4 | BO ->onboard pending group ->Bank details | when I add one Bank details, and click Add Bank no response | New | fixed | 86d0uqz4x
5 | BC->after onboard verified ->meeting | Both Attendance and Minutes of meeting, the group photo and resolution photo previous month are showing | New | fixed | 86d0uu0ja
6 | BC->after onboard group profile | remove all the edit icons in the group profile | New | fixed | 86d0uu6um
Ver 1.0.5(BC) Ver 1.2.3(BO) | 2025-03-11
1 | BC ->onboarding-> Member add | while adding member, that member have the account in the Canara Bank, select the branch and click the save button it's throw error "Please upload proof document" | New | fixed | 86d0v465v
2 | BC ->onboarding-> Member add | in the Device list remove Mantra 100 | New | fixed | 86d0v514b
Ver 1.0.6(BC) Ver 1.2.4(BO) | 2025-05-11
1 | BC->Existing SHG | if the pending group has bank details, in the bank details the proof is uploaded already but when I submit, it through error "Please upload proof document" | New | fixed | 86d0v465v
2 | BC->Existing SHG | in the group profile, PAN number verification it throw error message "Failed". | New
3 | BC ->onboarding ->Member add | while adding the aadhar details are in Masked but editing the aadhar details are visible | New | 86d0v465v | 86d0vjqv9
4 | BC ->onboarding->Cut off date | the cut off date must be previous day of onboarding | New | 86d0v465v | 86d0vjrjy
5 | BC ->onboarding ->Bank balance | it throw error "Bank balance update failed" | New | 86d0v465v | 86d0vjvzw
6 | BO ->Verification -> profile ->proof | change verify success toast message to "Proof verified successfully" | New | fixed | 86d0vp1yy
Ver 1.0.6(BC) Ver 1.2.4(BO) | 2025-06-11
1 | BC->Mint of metting->attendance | in the error message attenance spelling is not currect | New | fixed
Ver 1.0.7(BC) Ver 1.0.34(BO) | 2025-11-07
1 | BO->Existing SHG | both the pening and onboarded group must show in the list | New | fixed
2 | BO and BC | All the otp screen, the otp enter box must show above the keypad | New |  | 86d0wfb11
3 | BO ->Verification | It shows "no record found" | New | fixed
4 | BO ->Verification | in the list, only 5 groups are showing , not all the non verified group are showing. | New | fixed | 86d0wfc47
5 | BC->onboading->member profile | in the member add screen, and move back to the profile screen and clike otp, click the app back button, it moves to the main menu, again I open the group in the existing list and click the otp in member profile, click the submit button it throws error as "Failed" | New | fixed | 86d0wgh9x
6 | BO and BC->Onboarding->Member profile->Bank Details | After validating the bank details, in the note, change the "SHG name" to "member" | New | fixed | 86d0wh65h
7 | BC ->Onboarding->Member profile edit | if I add another bank, after validation, upload proof in camera, it show black screen | New | fixed | 86d0whde0
Ver 1.0.7(BC) Ver 1.0.34(BO) | 2025-11-08
1 | BC ->Onboarding->Member profile edit | if I add another bank, after validation, upload proof using gallary, it show black screen | New | fixed | 86d0wnb0q
2 | BO->Verification ->profile | I can verify the profile without verify the bank proof | New | fixed | 86d0wnbwm
Ver 1.0.8(BC) Ver 1.0.4(BO) | 2025-11-10
1 | BC->onboading->member profile | while adding the member, I add the bank details first member, I try to add bank details for the second member also. In the proof upload, it shows the first member proof. | New | fixed | 86d0x5u90
2 | BC and BO | After the phone call, the app crashed | New | fixed | 86d0xa7at
Ver 1.0.8(BC) Ver 1.0.5(BO) | 2025-11-11
1 | BO ->S/B Acount pending->esign document | The Kerala Bank document is showing, change to canara bank document | New | fixed | 86d0xpecb
2 | BO->SB Account pending->group photo->Gallery | The latitude and longitude are shown in the center of the photo | New | fixed | 86d0xpuum
3 | BO->SB Account pending->group photo->Camera | Only half latitude and longitude are showing | New | fixed | 86d0xpvhr
4 | BC ->onboarding ->Member add->Member proile edit | i can edit the bank details without click the edit button | New | fixed | 86d0uqx2y
5 | BC ->onboarding ->Member add | in the list of devices, if I select the Startek, it shows"unable to find Startek RD services app" | New | fixed
Ver 1.0.9(BC) Ver 1.0.5(BO) | 2025-11-12
1 | BO ->Verification-> in member profile->Bank details | Passbook verification shows "No record found." | New | fixed | 86d0y51dx
2 | BC -> onboarding-> member add | The member is duplicated (group name: Foundation Two) | New | fixed | 86d0y4zzx
3 | BO ->Verification ->Member profile ->proof | change verify success toast message to "Proof verified successfully" | New | fixed | 86d0y4ukd
4 | BC -> onboarding->profile | After uploading the proof document, it throw error when submit "Please upload the proof document" | New | fixed | 86d0y4x32
5 | BC -> onboarding->profile | the new proof are uploaded and submitted, after that, I come back from the member add screen to the profile, I click view it shows the old proof | New | fixed
6 | BO and BC | in the member profile and SHG profile, if I copy-paste any data, it reflects other fields | New | fixed
7 | BC ->After onboarding->Transaction->cash receipt | after the amount is entered and click submit, it loads in the same screen | New | fixed | 86d0y6xmb
Ver 1.0.9(BC) Ver 1.1.6(BO) | 2025-11-13
1 | BO->SB Account pending->group photo->Gallery | The latitude and longitude are not shown in tab | New | fixed
2 | BC -> onboarding->profile | the new proof are uploaded and submitted, after that, I come back from the member add screen to the profile, I click view it shows the old proof |  | fixed
Ver 1.0.9(BC) Ver 1.1.6(BO) | 2025-11-15
1 | BC ->member add | after entering the member information, click submit button it throw error "Failed" | New | Fixed
2 | BC ->Existing SHG | it throw error "Record not found" | New | Fixed
Ver 1.1.0(BC) Ver 1.1.8(BO) | 2025-11-17
1 | BC -> Onboarding->group profile->promoted by | I select the SRLM, but in the code enter it shows "NRLM code" | New | Fixed
2 | BC ->onboarding ->Bank balance | it throw error "Bank balance update failed" | re-open | Fixed | 86d0vjvzw
3 | BC ->New SHG->Existing to Canara Bank | If I enter the wrong customer ID and click fetch, it throws an error, after it moves to the main menu screen | New | Fixed
Ver 1.1.0(BC) Ver 1.1.0(BO) | 2025-11-18
1 | BC and BO->Member add | after entering the Aadhar number and clicking scan, "no responses " | New | Fixed | 86d106mkr
2 | BO->New to Canara Bank | After filled all the details and click submit, it throw error "Failed" | New | Fixed | 86d106nge
3 | BO->Verification | The newly created group in BC is not showing in the BO Verification | New | Fixed | 86d106p2e
Ver 1.1.0(BC) Ver 1.1.0(BO) | 2025-11-19
1 | Menu->FAQ | Update the FAQ | New |  | 86d10gcv3
Ver 1.1.0(BC) Ver 1.1.0(BO) | 2025-11-20
1 | BC->Member add | After completing the e-sign, it throws an error "Failed" | fixed | Fixed
2 | BO->SB Account pending->signature photo upoad | it throw error "Failed" | New
3 | BC ->onboarding ->Bank balance | it throw error "Bank balance update failed" | fixed | Fixed
Ver 1.1.34(BC) Ver 1.1.4(BO) | 2025-11-24
1 | BO-> Member add | if the member has no taluk in their Aadhar details, I can't add the member | New | Fixed
2 | BO->Verification->Balance sheet | In balance sheet "cash in hand, Excess of income over expenditure" not showing correctly | New | Fixed | 86d1283by
3 | BO->SB Account opening->Pending->Resolution photo | When upload the resolution photo, there are no responses | New
Ver 1.1.34(BC) Ver 1.1.4(BO) | 2025-11-25
1 | BC->Existing SHG->select the pending group | if I select the onboard complete group, it give no response, then I select the pending group after some time the otp screen shows. | New | Fixed
2 | BC->Login | it throws an error "Failed" | New | Fixed
3 | BC->Existing SHG->Verified group | the loading take some time | New
4 | BC ->Attendance | after capturing a photo and clicking submit, it loads and gives no responses | New |  | 86d12nf4g
Ver 1.1.34(BC) Ver 1.1.4(BO) | 2025-11-26
1 | BC->Member add | After fetched the finder print, the app crashed | New | fixed | 86d0mxjnq
2 | BC->Member add | in the Bank details proof, when I click the upload button, the image is not uploaded | New