## Mobile apk
Federal Bank Mobile Bugs
S.no | Module | Description | Status | Remarks | Bug Id
Version 1.0.56
1 | Onboarding | In the Onboarding add member profile, the annual income & net worth amounts have incorrect formation | new | Fixed
2 | SB Account Opening | In the SB Account Opening for the group in that e-sign for the president and secretary order changed | new | Fixed
Version 1.0.57 | 2025-05-23 |  |  | Fixed
1 | Meeting -> Minutes of meeting-> internal loan | After entering the loan amount and clicking the submit button, it show "please try again". | new | Fixed
Version 1.0.56 | 2025-05-26
1 | New SHG ¦¦ Onboarding ¦¦ Add Member ¦¦ Member Bank Details | On the Bank Details, "Account Number & Confirm Account Number" fields are not visible. | close | Fixed | 86cz2g64m
2 | BO Login ¦¦ Select Bank Branch | there is an extra space at the start of the Select Bank Branch list. | close | Fixed | 86cz2gn93
Version 1.0.58
3 | BC Login ¦¦ Branch Name ¦¦submit | On the BC Login, after selecting the Branch Name click the submit button, there is no response. | close | Fixed | 86cz2gyeh
Version 1.0.58 | 2025-05-27
1 | BC Login ¦¦ Onboarding ¦¦ Add Member ¦¦ Annual income | On the add member, Annual income validation seperater not working properly | new | Fixed | 86cz2wjrh
Version 1.0.61 | 2025-06-02
1 | After onboarding, SHG list->Bookkeeping->Deposit->Recurring Deposit ->new RD Account- | Installment amount not validated properly. | new | Fixed | 86cz57e1m
Version 1.0.61 | 2025-06-02
1 | After Onboarding->Group profile->Resolution for SHG Formation | After uploading the Resolution, there is no view button. If we reupload the image, then it shows the view button. | new | Fixed | 86cz5rxrk
Version 1.0.61 | 2025-06-03
1 | In MCP | In MCP, Member is duplicated >> Scenario is Member has multiple accounts, not considering the default account number for MCP. | new | Fixed | 86cz5tpud
Version 1.0.61 | 2025-06-04
1 | Minutes of meeting> Application of Bank Loan > Member account Validation | In member account validation, member duplicated--Scenario is Member has multiple accounts | new | Fixed | 86cz62e0z
Version 1.0.63 | 2025-06-10
1 | BO Login | can't login, It shows failed | New | Fixed | 86cz85r9n
Version 1.0.63 | 2025-06-24
1 | onboarding | if we change the 6-step formation date of the group to 2-step, after Onboarding, that group is duplicated. | New | Fixed | 86czd5eqj
Version 1.0.67 | 2025-07-02
1 | Add Member->Member profile | If I do not give the second ID proof and submit, in the Document Upload, it shows "please capture and upload all the above documents". | New | Fixed | 86czgr69z
2 | After Onboarding->Group profile | Resolution for SHG Formation and consents of onboarding there is no view button | New | Fixed | 86czgv4mm
3 | After Onboarding->Member Profile | Monthly Family income is incorrect format | New | Fixed | 86czgwjwu
Version 1.0.67 | 2025-07-03
1 | Add Member | if we try to add the same member twice, it gives the toast message Aadhaar number exists in the member profile submit process. | New | Fixed | Fixed
2 | Add Member->Member profile | in the Document Upload it show only Voter id formt. | old | Fixed | 86czgr69z
Version 1.0.68 | 2025-07-08
1 | After onboarding->Bookkeeping->Bookkeeping setting | In the title, it shows "Disbursement", change to "Bookkeeping setting". | New | Fixed | 86czjtk1q
Version 1.0.68 | 2025-07-16
1 | Add Member | it show "Technical failure internal to UNDAI Error Code k-955" | New | Fixed | Bank side issue
2 | BC Login - 8754029042 | Branch Name, it shows "No branch available" | New | Fixed | Fixed
Version 1.0.68 | 2025-07-16
1 | Add Member->Member profile->Aadhaar image | Internal APK error | New | Fixed
Version 1.0.71 | 2025-08-19
1 | Add Member | It shows "invalid or unresponsive from the server" | New | Fixed | 86d016g66
2 | SB Account Opening->e-sign | If I select the OTP option for e-sign, it shows "Something went wrong, please try again." | New | Fixed | 86d017uwj
3 | Add Member->Member profile | After upload the aadhaar photo and click verify it shows "check your internet connection." | New | Fixed | 86d017tuy
Version 1.0.71 | 2025-08-19
1 | Onboarding->Existing Federal Bank or New Federal Bank | if I select the Existing or New Federal Bank and click the back button "the app crash" | New | Fixed | 86d01muru
2 |  | While doing a 6-month transaction, it shows "Please try again" and logout | New | Fixed | 86d01nqka
3 | Group profile->Bank Details | we can give an initiated request multiple times | New | Fixed | 86d01nrz4
4 | Onboarding->Existing Federal Bank | it show "Some error accured, please check the parameteRS" | New | Fixed | 86d01q00a
Version 1.0.71 | 2025-09-08
New device
1 | Member add->Member profile | After entering all the information and clicking the submit button, it shows "Please choose any one bank" | New | Fixed
2 | date of birth for the nominee | "ok" button is invisible | New | Fixed
3 | e-sign | it shows "Bad Gateway" | New | Fixed
Version 1.0.71 | 2025-09-19
1 | SB Account Opening->SB A/c Pending | It shows "No records found" | New | Fixed | 86d0cdnqp
Version 1.0.73 | 2025-09-30
1 | SB Account Opening->SB A/c Pending->SB Account Queries | When I click chat, it shows "SAHAYOG data modified. Application will exit now". | New | Fixed | 86d0fj6eu
Version 1.0.73 | 2025-10-03
1 |  | when I click the back button from the member add to SHG profile, it shows "Please try again." | New | Fixed
Version 1.0.73 | 2025-10-07
1 | Member SB A/c opening | If i raise a query in the web, it does not show in the Member SB A/c | New | Fixed
2 | Member SB A/c opening | e-sign some time Aadhaar OTP not received | New | Fixed
Version 1.0.73 | 2025-10-08
1 | Log out | when we log-out it must move to sign-in page |  | Fixed
2 | Member financial | Cash Credit Outstanding must be in small letters |  | Fixed
3 | Balance sheet and Bank Balance | After entering the RD account number and the RD Balance, in the balance sheet, RD shows "0", then check in the Bank Balance screen the RD account number and the RD Balance are empty. | New | Fixed | 86d0jc1b5
Version 1.0.71 | 2025-10-09
1 | Membre SB account->chat | After enter the quary and click send button it shows "Failed to add response" | New | Fixed | 86d0jtt0v
Version 1.0.71 | 2025-10-10
1 | Membre SB account->chat | After typing the message and clicking send message not send keypad is closed, again I click the send button, then it sends | New | Fixed | 86d0k7cwr
Version 1.0.71 | 2025-10-13
1 | Member SB A/c opening | After verifying in the approval, if I create new ticket in approvel, there is no response on the mobile | New | Fixed
Version 1.0.72 | 2025-10-14
1 | Member SB A/c opening | After the ticket closed, in the member's SB A/c, it shows approval pending, if I clicke the member it move to E-sign page. | New | Fixed | 86d0m450g
Version 1.0.72 | 2025-10-16
1 | Member Add | In the SHG profile the group type is female, but I can add male as a member | New | Fixed | 86d0mxjnq
2 | login->forgot pin | In the confirm Pin it shows "failed" | New | Fixed | 86d0mxn6r
Version 1.0.75 | 2025-10-16
1 | memebr SB Account->signature upload->e-sign | I upload the signature photo for the member SB opening, if I clike the mobile back button,again it move to the signature upload screen. | New | Fixed
2 | memebr SB Account->signature upload->e-sign | for one member after e-sign, after success message, app crash | New | Fixed
Version 1.0.76 | 2025-11-27
1 | Onboarding->New to federal bank | give notes to the Remarks | New | Fixed | 86d13j5un
2 | Onboarding->New to federal bank | If I select "yes" to, Whether SHG SB Account is to be Created?, the Bank Details must be invisible | New | Fixed | 86d13j6jj
3 | Onboarding->Member add | Edit the member profile click submit buttom, it throw error "Please verify the voter id" | New | Fixed | 86d13jfkn
Version 1.0.76 | 2025-11-28
1 | Onboarding->New to federal bank->SHG Profile->Bank details | While validating the bank details, it throws an error "Failed" | New | informed | fixed
2 | Onboarding->New to federal bank->SHG Profile->Send otp | It throws an error, "Please check your network connection" | New | informed | fixed
3 | After Onboarding->Transaction->cash receipt | After entering the amount and saved, if I close or go back to the home screen and come back, the paid member count is not showing correctly | New | Fixed | 86d13vcqh
4 | After Onboarding->SHG Profile->Bank details | After validating the dank detail, without clicking the edit button, I can edit the bank details | New | Fixed | 86d13vped
| After Onboarding->SHG Profile-> Registration Certificate Document upload | in the title, it shows "Consent Onboarding." | New | Fixed | fixed
6 | Onboarding->New to federal bank->SHG Profile->Bank details Note | add this as a note "Enter bank details only if the SHG already has an account number; otherwise, leave it blank." | New | Fixed | 86d13z341
7 | Onboarding->New to federal bank->SHG Profile->Remarks note | add this as a note : "Reason is required, if total member are below 10." | New | Fixed | 86d13z3um
8 | Onboarding->New to federal bank->SHG Profile->Consent for onboarding note | Note is not showing | New | Fixed | 86d13z46r
9 | Onboarding->New to federal bank->SHG Profile->Member add | changes the terms and conditions must be same as Aadhar number enter terms and conditions | New | Fixed | 86d13z4t2
Version 1.0.77 | 2025-12-01
1 | MCP | Document upload, using the camera, edit the image brightness, and click rotate the brightness is not change | New | Fixed
Version 1.0.79 | 2025-12-02
1 | After Onboarding->Profile->Group profile | If I select the profile, the group profile information is not showing, and the app crashes | New | fixed
Version 1.0.79 | 2025-12-02
1 | Onboarding->Member add | after entering the member details and clicking the submit button, it throws an error "Failed" | New | Fixed
Version 1.0.80 | 2025-12-16
1 | BO ->login->mobile number verification screen | In the otp screen, it shows "otp verified failed." | New | Fixed
2 | Onboard->Member add->Bank Details | In the Bank name list, need none option | New | Fixed
3 | Onboard group->profile ->add Bank | After adding the bank details and updating the profile, come back, the bank detail are not showing in the profile | New | Fixed | 86d1a5wge
Version 1.0.80 Version 1.0.82 | 2025-12-17
1 | Onboard-->Member add->member profile | If I select "yes" to Whether Interested in Opening FBL SB. in the state selection, it shows "Please check your network connection." | New | fixed
2 | Member add->Member profile | when I click the submit button, it shows the error "Failed." | New | Fixed | 86d1aexna
3 | Ver 1.0.82->Member add | After fingerprint, it shows an error "Error Code Invalid Security Token." | New | Fixed | 86d1aexzg
Version 1.0.82 | 2025-12-18
1 | Member add->otp enter | When I click resend otp it throw error as "Error Code 378" | New | Fixed
2 | Member add | I can add a other member using my mobile number | New | Fixed
Version 1.0.84 | 2025-12-18
1 | login | in the BSNL Network, after entering the Pin it shows toast messages as "Please check your network connection." | New | Fixed | 86d1b3j3g
2 | Member add->Member profile | in the profile image upload, it shows toast messages as "Verify successfully". | New | Fixed
Version 1.0.87 | 2025-12-22
1 | MCP | the Annual Income is not reflected in the MCP Annual Income | New | Fixed | 86d1bv111
2 | CRIF Score view | After viewing the score and clicking the next button, the app crashed | New | Fixed | 86d1bv17e
3 | Onboaed->Member add | PAN verification shows "Failed." | New | Fixed | 86d1bv1u5
4 | After Onboarded ->Member profile | That member is added using PAN, but when I view the profile, it shows Voter id is mandatory |  | Fixed
Version 1.0.88 | 2025-12-23
1 | After onboard ->group profile->formation date edit | In the calendar, it must pin the current formation date. | New
2 | After onboard ->Last Transaction date select | In the calendar, it must pin the current last month transaction date. | New
3 | SB A/c e-sign | It shows an error as "you do not have access to this url" for the new group | New | fixed | 86d1c7w8n
4 | Bookkeeping->Payment->Disbursement->Select Payment | The MFI loan is not showing but white space is showing | New | Fixed | 86d1c8j2q
Version 1.0.90 | 2025-12-24
1 | Onboarding->Member add->Voter id Verify | It throw error as "insufficient cred score." | New
2 | MCP | The "save button" is not enabled | New | fixed
3 |  | Sometimes the app crashed | New
4 | After Onboarded ->Member profile | That member is added using PAN, but when I view the profile and click submit, it shows please select accept /manual reconfirm for Voter id. | New | fixed
5 | Ver 92->SB A/c | After uploading the resolution and Signature photo and moving to the e-sign pending list, it shows "failed." | New | Fixed | 86d1cfg5w
6 | BO->Onboard->Member add using otp | After entering the Aadhaar, in the otp generation, it shows "otp generation failed" | New | Bank side
Version 1.0.92 | 2025-12-25
1 | After onboard->Member profile->Bank detail | after add the other then federal bank details and clicking the submit button in the profile, it shows "Failed" | New | Fixed | 86d1cmr54
2 | Application for Bank loan->Inter-SE Agreement date | In the calendar, the current month date must show | New | Fixed | 86d1cnbed
Version 1.0.94 | 2025-12-26
1 | Member Add-> PAN or Voter id upload | In the upload preview, need to give some space between images | New | Fixed | 86d1cuz8m
Version 1.0.95 | 2025-12-29
1 | Onboard->Member add->Bank Details | The state and district are in mandatory but I can submit the member profile without enter the state and district | New | Fixed | 86d1dcv20
2 | Member profile | If the profile picture was taken by the front camera, the picture is not clear | New | Fixed | 86d1dcukr
Version 1.0.95 | 2025-12-30
1 | BO -> after onboard->member profile->bank details | after adding the bank detail in the member profile and submit, the bank detail is not update in the member profile | New | Fixed | 86d1djymf
2 | Minutes of meeting->Application for Bank loan->Grading | Number 8, 14, 15, not all the choices are showing | New | Fixed | 86d1dqtw5
3(Ver 1.0.96) | Minutes of meeting->SHG profile->Net worth | the comma are not correct separation for the net worth amount | New | Fixed | 86d1dqt7h
Version 1.0.97 | 2025-12-31
1 | onboarding->SHG Profile | in the member add and come back to the SHG profile, the networth is empty | New
2 | MCP->Inter-se Agreement capture | The image taken by the Gallery is not clear | New | Fixed | 86d1dxxp3
3 | MCP->Inter-se Agreement capture | In camera, the flash is not working | New | Fixed | 86d1dxxa5
Version 1.0.97 | 2026-01-01
1 | Member adding->PAN or Voter id document upload | In camera, the flash is not working | New | Fixed | 86d1e3rh7
2 | Onboaed->Member add | After add the member and clicking edit for that member,Remove the mandatory syembol in voter id | New | Fixed | 86d1e3tqr
Version 1.0.97 | 2026-01-02
1 | Member financial | after enter the amount in member's financial and click submit button, it throw error "Please try again" | New | Fixed
2 | MCP ->Inter-SE Agreement capture | When I select a date from the calendar, the app crash | New | Fixed | 86d1ejbk6
Version 1.0.99 | 2026-01-05
1 | After onboarding->Group profile | Whether interested in opening an SB account option is not showing after onboarding | New | Fixed
Version 1.0.102 | 2026-01-06
1 | Group SB Account opening | Remove the Group photo upload in the Group SB account opening | New
Version 1.0.103 | 2026-01-07
1 | MCP->CRIF View | it shows "Failed" | New | Fixed
2 | Group SB Account Document | In the document, for the group photo and signature titles are missing | New | Fixed
Version 1.0.105 | 2026-01-08
1 | BO->Onboard->Member Profile | If I select "Yes" for "Whether interested in opening an SB account", the state and District are showing "No" | New | Fixed | 86d1gwvex
Version 1.0.106 | 2026-01-09
1 | MCP->Inter-se Agreement capture->Gallery | The image taken by the Gallery is not clear | New | fixed | 86d1dxxp3
Version 1.0.108 | 2026-01-19
1 | Sign in | All the details are in left side of the screen, only in the tab | New | fixed
2 | SHG Profile -> Bookkeeping->Payment->Disbursement | Internal Loan Amount is not showing | New | Fixed
Version 1.0.111 | 2026-02-04
1 | Onboarding->Member add->PAN id Verify | PAN Verify it shows "Failed" | New | fixed
2 | Onboarding->Member add->authorized signatory | after give authorized signatory "yes" in the Aadhaar info, I can edit the authorized signatory in the Member profile | New | fixed | 86d1uytvm
3 | BCQC Login->After Onboarding | I complite the onboarding in 2 step but when i open again shows up to Balance sheet | New |  | 86d1uyuv6
4 | Onboarding->Member add->Aadhaar info->Designation | it shows "No designation's were found" | New | fixed
5 | SHG List | in the group, the Reason is showing empty, if i expand the group status the Reason is missing | New | New | 86d1v28jk
6 | After onboard ->group profile->Bank state and District | the State and District are not showing | New | fixed | 86d1v2h4q
7 | After onboard ->Member SB A/c opening | The member select "Yes" for SB A/c opening, that member is not showing | New | fixed | 86d1v2j2e
Version 1.0.111 | 2026-02-05
1 | Onboarding->Member add->Aadhaar Verify | It shows error message as "Please check your network connection " | New | fixed | 86d1vhvp8
Version 1.0.110 | 2026-02-06
1 | After Onboarding->Member add | After onboarding, if I came back to member profile, change the Whether interested in opening FBL SB Account as yes, click send otp it shows an error as "Please check your network connection" | New | fixed | 86d1w62yz
Version 1.0.110 | 2026-02-09
1 | OTP | the otp is not woring, it throw an erroe as "Please check your network connection" | New | fixed
2 | Member Add | onboarding validation failed |  | fixed
Version 1.0.110 | 2026-02-10
1 | Onboarding->Member add->Voter id | The voter id is validated only in the member profile submit button, not in the Aadhaar info proceed, so if the member gives the same voter id for two members, it can't be edited in the member profile | New |  | 86d1xhnkd
2 | Onboarding->Member add->Designation | The Designation is validated only in the member profile submit button, not in the Aadhaar info proceed, so if the member gives the same Designation for two members, it can't be edited in the member profile | New |  | 86d1xhz88
Version 1.0.112 | 2026-02-11
1 | Minutes of meeting->Attendance | Select all check box is showing at the center only in the tab | New |  | 86d1y0w7f
2 | app crash | Randam app crash | informed
Version 1.0.113 | 2026-02-12
1 | Onboarding ->Member add-> Edit Mobile profile->OTP | I can't cancel the entered otp | New |  | 86d1y9w6f