## Sheet1
NRLM Mobile Bugs
S.no | Module | Description | Status | Remarks | Bug Id
Version 1.0.0 | 2025-12-05
1 | Member financial | I add three members and delete one but in the memebr financial it show three number | New | Fixed | 86d16j1wk
2 | Member add->member profile | after add the member and edit, the taluk is empty | New | Fixed | 86d16j2hk
3 |  | The app is showing in full screen, the mobile back button and app home, SHG button are overlapping in Android version 15,16 | New | Feedback | 86d16j43b
4 |  | Add apk version to the login screen and menu | New | Fixed | 86d16j4b6
5 | Cutoff date | after entering the cutoff date and move to the member's financial, and come back to the cuttoff date, it show "null" | New | Fixed | 86d16j4wd
6 | cuttoff screen->Add bank details | No responses when I click the Add Bank Details | New | Fixed | 86d16j54k
7 | Menu | the name and last login are showing empty | New | inprogress | 86d16jky4
8 | Menu-> login nrlm image | Click the profile image, no response | New | inprogress | 86d16jnrw
9 | Member add | The member count is not validated | New | Fixed | 86d16jz84
Version 1.0.5 | 2025-12-15
1 | login page | If I click the back button on the login screen, it moves to Anniyam logo screen | New | Fixed | 86d19kvt0
2 | Menu | The version must show at the bottom | New | Fixed | 86d19qmye
3 | Onboard->Member add | After entering the details and clicking the save button, the app closed | New | Fixed | 86d19qnnd
Version 1.0.5 | 2025-12-16
1 | login | After enter the Pin, It shows toast as "To many OTP request" | New | Fixed | 86d1a4nj5
Version 1.0.0 | 2025-12-18
1 |  | add the session timeout | New | Resolved | 86d1aw65t
2 |  | I can do auto-rotate | New | Fixed | 86d1aw95g
3 |  | In the sign-in screen, the version is 1.0.5 and in menu version 1.0.0, give dynamics version |  | Fixed | 86d1awgtb
Version 1.0.5 | 2025-12-19
1 | SHG Profile | in the pening group, the SHG Code is not showing | New | Fixed | 86d1b70n4
2 | shg list and pending list | SHG Code is not showing | New | Fixed | 86d1b7137
Version 1.0.1 | 2026-01-12
1 | Onboarding->SHG Profile->Number of Linkage | only 1 linkage is showing | New | Fixed | 86d1j54qa
2 | Onboarding->SHG Profile->Primary Contact Mobile Number | Need to verify the Mobile number | New | Fixed | 86d1j55dv
3 | Onboarding->SHG Profile | After moving to the member adding screen, if I come back to the SHG profile, I can’t update the SHG Proile | New | Fixed | 86d1j56kw
4 | Onboarding->SHG Profile->Location Type | In location type I select "Town Panchayat" and complet the SHG Profile, come back to edit the profile it shows as Villege and Ward as "Null" | New | Feedback | 86d1j5amz
5 |  | if I click Home or SHG, it shows a toast message "Unknown Error." | New | Fixed | 86d1j5b2g
6 | Onboarding->SHG Profile | I can submit the SHG Profile, I give no responses when I click the save button | New | Fixed | 86d1j5cmf
7 | Onboarding->Member profile | Sometimes member adding is not working, when I click the save button, it loads | New | Fixed | 86d1j984y
8 | Member adding | Need to get OTP Verification for Member delete. | New | Fixed | 86d1j970u
9 | Onboarding->Member profile | Member profile image is empty when I edit the member profile. | New | Fixed | 86d1j98tn
10 | Onboarding->Member profile | I can give the designation as President for both members | New | Fixed | 86d1j9akm
Version 1.0.1 | 2026-01-13
1 | Setting->update PIN | it shows toast message as "Update PIN clicked" | New | Fixed
2 | side menu->Profile | In the profile, all the details are empty | New | Fixed
3 | Onboarding->Member profile | The app crashed when I clicked the "Add member" | New | Fixed | 86d1jp2d8
|  | Give the App Verssion Dynamically | New | Fixed | 86d1jp33b
4 | Member add-> Mobile number verification OTP | not aligned at the center, in tab |  | Fixed | 86d1jq3jg
5 | Member add-> Mobile number verification OTP | I can't cancel the entered otp | New | Fixed | 86d1jq3ua
6 | Member add-> Delete member->OTP | not aligned at the center, in tab | New | Fixed
7 | Member add-> Delete member->OTP | I can't cancel the entered otp | New | Fixed
8 | Onboarding->Member add | The app crashed when I clicked the edit member | New | Fixed | 86d1jr02a
Version 1.0.1 | 2026-01-14
1 | cut-off date screen->Add bank details | It give no response when I click Add bank details | New | Fixed | 86d1k2mpq
2 | cut-off date screen->Add Loan->Group Loan->MFI | in that I can select Repayment yes or no, but when I click the MFI it gives no response. | New | inprogress
3 | cut-off date screen->Add Loan->Group Loan->Federation | it only shows the repayment type selection option only | New | inprogress
4 | cut-off date screen | I can submit the SHG Loan without select the cut off date | New | Fixed | 86d1k2kd0
5 | After Onboarding->Group proile | I can’t update the SHG Proile | New | Fixed | 86d1k2m1k
6 | After Onboarding-> Meeting->Minutes of meeting | Tenure list, in the search, it shows as "Select purposes of loan." | New | Fixed | 86d1k50qb
7 | After Onboarding-> Meeting->Minutes of meeting | When I do not complete the internal lone, I move to the home screen and come to a meeting, and the pending process is not showing | New | inprogress | 86d1k4mj8
Version 1.0.4 | 2026-01-19
1 | After Onboarding->Transaction->Cash Receipt | After entering the Amounts for the member, I click the mobile back button, it does not move to the SHG home page | New | Fixed | 86d1mqvxx
2 | cutt-off screen->Add loan | The rate of interest needed the decimal point. | New | Fixed | 86d1mvxda
3 | Onboarding->SHG Profile | Come back to the SHG Profile, number of linkage is showing null | Old | Backend | 86d1mw447
4 | Onboarding->Member finances | After deleting the member and moving to the Member finances, it shows the deleted member also in the member finances | New | Fixed | 86d16j1wk
5 | Onboarding->SHG Profile | The bank details are duplicated. | New | Fixed | 86d1mw4hd
6 | Onboarding->Member Financial | If I try to enter more than 99,999, not all the digits are showing (1,00,00 it shows 1,00,00) | New | Fixed | 86d1mvw91
Version 1.0.4 | 2026-01-20
1 | Login screen->OTP Enter | I can't cancel the entered otp | New | Fixed | 86d1ncb73
2 | Transaction->Cash Receipt | Click the submit button, and it gives no responses | New | inprogress
3 | After onboarding->SHG Profile | Bank details duplicated | New | Fixed
4 | Transaction->Beneficiary | if Iclick add bank, it shows an error as "Unknown Error." | New | Fixed | 86d1nbu4r
5 | Onboarding->SHG Profile | All the dropdown searches, I can enter Special character | New | Fixed | 86d1nbrkd
6 | Onboarding ->Member add->Member profile->Address | The district is selected, but when I try to select the Block, it shows an error as"Please select district." (only in Coimbatore, Salem) | New | inprogress
7 | Onboarding->SHG Profile | Not all the masters are showing | New | inprogress
8 | Onboarding->SHG Profile->PAN Number | it give no responces i enter an invalid PAN Number and submit | New | Fixed | 86d1ncarn
9 | Onboarding->cut-off date screen | In error toast message it shows as "Please choose cutoff date" change this to " Please choose cut-off date" | New | Fixed
10 | Onboarding->Member Profile->Gender | In the droupdown search it shows as "Select Group type" change to "Select Gender type" | New | Fixed | 86d1ncw5x
11 | Onboarding->Balance sheet->Excess of income over expenditure | If I try to enter 1,00,00,000 it shows 1,00,00,00) | New | Fixed | 86d1nd0gj
Version 1.0.5 | 2026-01-21
1 | Onboarding ->Balance sheet | the balance sheet amount is not showing if I go to the home screen and come back to pending group | New | Backend | 86d1nnpru | s
2 | After onboarding-> Minutes of Meeting | Only the Request for an internal loan is working, if I select other it shows "Minutes of meeting submitted successfully" and move to the SHG Home screen | New | Feedback | 86d1np23t
3 | Ater Onoarding->SHG Profile | Add the bank details, and update the SHG Profile. It gives no responses | New | Fixed | 86d1nphz5
4 | Onboard->SHG Name | In SHG Name, it have space at the end of the name | New | Fixed | 86d1nqnbz
5 | Onboarding->Balance sheet | after click the submit button, it gives no responces | New | Backend | 86d1nttr2
6 | Onboard->Member profile->Address->Ward | In the address, Ward is not mandatory, but in the communication address, if I select "yes" without selecting a ward, it give toast message as "Please provide all address fields and try again" | New | Resolved | 86d1nu3nm
7 | Onboard->Member profile->Town Panchayat | The Mandatory symbol is not in red color | New | Fixed | 86d1nu5m5
8 | Onboarding->Member profile | After editing the member, that member is not showing in the Member profile list | New | Fixed
9 | After onboarding->Bookkeeping-> Receipt reports | it give no responses when I click the Receipt reports | New | Feedback | 86d1nvbgr
10 | After onboarding->SHG Home->Auditing | The selected End and Auditing date are showing in the Start date | New | Fixed | 86d1nvtwn
11 | After onboarding->SHG Home->Auditing | If I click the Submit button without entering any date, it gives no toast messages | New | Resolved | 86d1nvvhq
Version 1.0.5 | 2026-01-22
1 | In the 6 Months Transaction | The last transaction date is not updated (ex : the last transaction date is 03/11/2025, I changed this date to 29/12/2025, and done to Attendance after i go SHG List and came to the same group, now the last transaction date is 03/11/2025 | New | Fixed | 86d1p705y
2 | After onboarding->SHG Profile | After add the Bank details, update the shg profile gives no responses. | Reopen | Fixed | 86d1nphz5
3 | Onboarding->Number of linkages | The search is not working properly (Ex : if search 2 it shows 2, 8, 12) | New | Resolved | 86d1p7euj
4 | Onboarding->Meeting time->AM or PM | remove the search | New | Resolved | 86d1p8mkb
5 | Onboarding->SHG Profile | For all Location types, it shows error messages as "Please select taluk" | New | Fixed | 86d1p9z7e
Version 1.0.5 | 2026-01-23
1 | Onboard->SHG profile->Town Panchayat | The Mandatory symbol is not in red color | New | Resolved | 86d1pjwez
2 | Onboarding->Bank Balance->Fixed Deposit Balance for FD and RD | I can enter 10,000 only. If I try to enter more than 10,000, it shows as (10,000 it shows 1,00,00) | New | Resolved | 86d1pjx34
3 | Onboarding->Bank Balance->Saving Bank account balance | Remove the mandatory symbol in Saving Bank account balance (SB) | New | Resolved | 86d1pjxn3
4 | Onboarding->Bank Balance | After filling all the fields in SB, FD, RD , when I click the save button, it throw error message as "Please enter all the FD fields" | New | Resolved | 86d1pjy6e
5 | Onboarding->Bank Balance | If I not enter RD or SB field and click Save button it shows as "Please enter all the FD fields" | New | Resolved | 86d1pk0cu
6 | After onboarding-> Minutes of Meeting-> internal loan | In the installment start date, it shows upto Cut off date for every transaction | New | Feedback | 86d1pk3p0
7 | After onboarding-> Minutes of Meeting-> internal loan>Rate of Interest | I can enter 10000 on the Rate of interest | New | Resolved | 86d1pkfx7
8 | Onboarding->SHG Profile | if I come back from Member add screeen to the SHG profile, the Town Panchayat, Ward, and Number of linkage are in Null | New | Fixed | 86d1pmmfn
9 | After onboarding->SHG Profile->Bank Details | If I add two bank details, the bothe are in default, I can't change the Default account | New | Resolved | 86d1pmva9
10 | Onboarding->SHG Loan->Group Loan->Bank | if I select the bank it shows all the bank loan fields, and but if I select the MFI and select the Bank again, it show only MFI | New | inprogress
Version 1.0.6 | 2026-01-30
1 | After Onboarding->Transaction->Cash Receipt | Member Count is showing zero, If I enter the receipts amount for the first member, then the member count is showing correctly. | New |  | 86d1tzqgy
2 | Member add->member profile | The profile image is not showing when I edit the member profile | New | Fixed
3 | After onboarding ->Group profile->Date of meeting at every month | The meeting date is showing "null." | New | Re-open | 86d1u1hfe
4 | After onboarding-> Minutes of Meeting | The meeting count is showing "zero" for every month meeting | New |  | 86d1u243e
5 | After onboarding-> Minutes of Meeting | The Last Meeting Date and Transaction Date are showing the same date | New |  | 86d1u2r1z
Version 1.0.6 | 2026-02-03
1 | SHG List | The onboarded and pending not showing in center, only in tab | New
Version 1.0.7 | 2026-02-04
1 | SHG List | Internal server error. Please please try again | New | Fixed
Version 1.0.9 | 2026-02-05
1 | Main Menu->Onboarding | it shows error message as "not found" | New |  | 86d1veutu
2 | Login ->Enter PIN | move the "Forgot PIN?" to center | New |  | 86d1vepmk
3 | SHG Profile->Bank Details | If I select the Bank name as None and click Submit, it shows "Please provide Branch" | New |  | 86d1vfzze
4 | Onboarding->Bank Balance | i have two bank, if i enter SB, FD, RD for the first bank, then I select the second bank it shows the first bank SB, FD, RD | New |  | 86d1vk7zw
Version 1.0.9 | 2026-02-06
1 | SHG List ->Pending and Onboarded list | If the group has the account details that account opening date next date is shown as last trans date for both the Pending and Onboarded group | New |  | 86d1w5kmq
Version 1.0.11 | 2026-02-19
1 | Onboarding->SHG loan->Group Loan | if i click the mobile back button in the group loan it shows error message as "Not Found" | New |  | 86d210rkc
2 | After onboarding ->Group profile->Date of meeting at every month | The meeting date is showing "null." | Old | Re-open | 86d1u1hfe
3 | Onboarding->SHG Profile | Come back to the SHG Profile, number of linkage is showing null | Old |  | 86d1mw447