## Sheet1
NRLM Over View
S.no | Module | Description | Status | Remarks | Bug Id
Version 1.0.4 | 2026-01-19
1 | Onboarding->SHG Profile | Not all the masters ware showing | new
2 | After Onboarding->Transaction->Cash Receipt | After entering the Amounts for the member, I click the mobile back button, it does not move to the SHG home page | New |  | 86d1mqvxx
3 | cutt-off screen->Add loan | The rate of interest needed to be two numbers before and after the decimal point | New
4 | cut-off screen, member add, | Edit and delete are not working | New
5 | Onboarding->SHG Profile | Come back to the SHG Profile, number of linkage is showing null | New
6 | Onboarding->member add | After deleting the member and moving to the Member finances, it shows the deleted member also in the member finances | New
7 | After Onboarding-> Meeting->Minutes of meeting | When I do not complete the internal lone, I move to the home screen and come to a meeting, and the pending process is not showing | New |  | 86d1k4mj8
8 | cut-off date screen | I can submit the SHG Loan without select the cut off date | New |  | 86d1k2kd0
9 | Onboarding->Memner Financial | If I try to enter more than 99,999, the digits are not showing | New
10 | Onboarding->SHG Profile | The bank details are duplicated. | New |  | 86d1mw4hd
Version 1.0.5 | 2026-01-30
1 | After onboarding-> Minutes of Meeting-> internal loan | In the installment start date, it shows upto Cut off date for every transaction | New |  | 86d1pk3p0
2 | After onboarding-> Minutes of Meeting-> internal loan>Rate of Interest | I can enter 10000 on the Rate of interest | New |  | 86d1pkfx7
3 | After onboarding->SHG Profile->Bank Details | If I add two bank details, the bothe are in default, I can't change the Default account | New |  | 86d1pmva9
4 | After Onboarding->Group proile | if I enter PAN number and edit the address, the entered PAN number is not showing | New
5 | After Onboarding->Group proile | In the address the town panchayat and ward are showing "Null" | New